## Rates 1st
There is no need to sort or keep in order this table. Fill top to Bottom. If you run out of room in the table - no bother just continue to add at the bottom
Fuel Price |  | This Column needs to be Unique to be able to identify the item quickly and easily | If an item does not have a value for a particular column then leave relevant cell blank | [12 empty] | Preparation Table
Labour Oncost %
Supplier | Resource | Details | Base Rate | Plant Depn | Allowances | Fuel Consumption Liters/Hour | Fuel | GETs | Lube | Total Rate | Unit | Drop Downs | INDICATIVE FUEL BURN RATES |  |  | Resource | Contractor | Equipment | Labour | Material
[7 empty] | 0 |  |  | 0 |  | Labour | Grader | 12H | 20.5714 | Contractor | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  | 0 |  | Equipment | Grader | 12G | 20.5714 | Equipment
[7 empty] | 0 |  |  | 0 |  | Material | Loader | 950 | 6.86 | Labour
[7 empty] | 0 |  |  | 0 |  | Contractor | Loader | 970 | 8.57 | Material
[7 empty] | 0 |  |  | 0 |  |  | Integrated Toolcarrier | IT 28 | 6.8571
[7 empty] | 0 |  |  | 0 |  | /man/day | Skid Steer |  | 5.7143
[7 empty] | 0 |  |  | 0 |  | /man/meal/day | Backhoe |  | 5.7143
[7 empty] | 0 |  |  | 0 |  | Day | Tractor | Broom/slasher | 5.7143
[7 empty] | 0 |  |  | 0 |  | Ea | Excavator | 30t | 11.4286
[7 empty] | 0 |  |  | 0 |  | Hour | Excavator | 30t + breaker | 11.4286
[7 empty] | 0 |  |  | 0 |  | Item | Excavator | 12t | 8.5714
[7 empty] | 0 |  |  | 0 |  | KL | Excavator | 3.5t | 6.8571
[7 empty] | 0 |  |  | 0 |  | Km | Excavator | 18t rubber tyre | 10.2857
[7 empty] | 0 |  |  | 0 |  | Litres | Fuel Truck |  | 2.8571
[7 empty] | 0 |  |  | 0 |  | m | Rigid Truck | 6W Watercart / Tipper | 9.7143
[7 empty] | 0 |  |  | 0 |  | m2 | Rigid Truck | 8W Watercart / Tipper | 9.7143
[7 empty] | 0 |  |  | 0 |  | m3 | Prime Mover + single | Watercart/Sidetipper/Float | 8.5714
[7 empty] | 0 |  |  | 0 |  | Month | Prime Mover + double | Watercart/Sidetipper/Float | 9.7143
[7 empty] | 0 |  |  | 0 |  | Sheets | Prime Mover + triple | Watercart/Sidetipper/Float | 10.8571
[7 empty] | 0 |  |  | 0 |  | Sum | Hiab Truck | 8t | 8.5714
[7 empty] | 0 |  |  | 0 |  | Tonne | Tilt Tray Truck |  | 8.5714
[7 empty] | 0 |  |  | 0 |  | Week | Mobile Concrete Plant
[7 empty] | 0 |  |  | 0 |  |  | Smooth Drum Roller |  | 6.8571
[7 empty] | 0 |  |  | 0 |  |  | Multi Roller |  | 6.8571
[7 empty] | 0 |  |  | 0 |  |  | Padfoot Roller |  | 6.8571
[7 empty] | 0 |  |  | 0 |  |  | Light Vehicle |  | incl
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
[7 empty] | 0 |  |  | 0
| Contractor | [5 empty] | 0 |  |  | 0
| Equipment | [5 empty] | 0 |  |  | 0
| Labour | [5 empty] | 0 |  |  | 0
| Material | [5 empty] | 0 |  |  | 0
WSFNQuoteV6

## Summary
Quote Template
Shire of xxx/ road | SLK Start | SLK Finish
CONSTRUCTION ESTIMATE MAIN SUMMARY
SCHEDULE 1 - CONSTRUCTION ITEMS
GENERAL REQUIREMENTS | 0
EARTHWORKS | 0
DRAINAGE | 0
PAVEMENTS and SURFACING | 0
TRAFFIC FACILITIES | 0
MISCELLANEOUS | 0
0
SCHEDULE 2 - PROVISIONAL SUM ITEMS
PROVISIONAL SUMS | 0
0
Total Cost (GST Exclusive) |  | 0 | $/km
| Shire Contribution | 0

## Schedule
Shire of xxx/ road SLK to
| Project General Information | Duration weeks |  | Hours per Day
Quote Template
Item | Description | Unit | Qty | Rate | Amount | 0
SCHEDULE 1 - CONSTRUCTION ITEMS
GENERAL REQUIREMENTS | SERIES 300 - EARTHWORKS
CONDITIONS of CONTRACT
GR_01 | Cost of Certificates of currency to sustain the contractual obligations. | Sum | 1 | 0 | 0
Utilities and Services
GR_02 | Location, Relocation, Protection of Utilities and Services | Sum | 1 | 0 | 0
MOBILISATION and DEMOBILISATION of PERSONNEL, PLANT and EQUIPMENT
GR_03 | Cost relating to in mobilisation and Demobilisation of Personnel, Plant and Equiptment to and from the worksite facilities.(including their RDO breaks) | Sum | 1 | 0 | 0
SITE FACILITIES (Accommodation and Meals)
GR_04 | Cost relating to accommodation, meals, maintenance and Management of the on-site facilities for the duration of the contract. | Sum | 1 | 0 | 0
SURVEY and AS-CONSTRUCTED RECORDS
GR_05 | Cost of Setting out the works and the Submmission of the As-Constructed records and plans | Sum | 1 | 0 | 0
MANAGEMENT and SUPERVISORY REQUIREMENTS
GR_06 | Cost of relating to preparation, submission, implementation, execution and supervision of the Construction / Project Management Plan and Construction programme | Sum | 1 | 0 | 0
QUALITY ASSURANCE and TESTING
GR_07 | Cost of Quality Assurance Testing, pavement testing by NATA approved company | Sum | 1 | 0 | 0
OCCUPATIONAL SAFETY and HEALTH
GR_08 | Cost relating to the preparing, submitting, reviewing updating implementing and maintaining the Occupational Safety and Health Plan for the duration of the contract. | Sum | 1 | 0 | 0
ENVIRONMENTAL REQUIREMENTS
GR_09 | Cost relating to the preparing, submitting, reviewing updating implementing and maintaining the Environmental Management Quality Plan for the duration of the contract. | Sum | 1 | 0 | 0
TRAFFIC MANAGEMENT REQUIREMENTS
GR_10 | Cost relating to the preparing, submitting, reviewing updating implementing and maintaining the Traffic Management Plan for the duration of the contract. | Sum | 1 | 0 | 0
PIT REHABILITATION
GR_11 | Cost of rehabilitation of Stockpile and or Borrow Pit Area | Sum | 1 | 0 | 0
CONSTRUCTION WATER
GR_12 | Costs Relating to the Provision of construction water | Sum | 1 | 0 | 0 | 0
To Main Summary |  |  |  |  | 0
EARTHWORKS | SERIES 300 - EARTHWORKS
Item | Description | Unit | Qty | Rate | Amount
301 - CLEARING
CLEARING
Ec_301.01 | Clear and cut the designated construction area, and table drains of all vegetation and topsoil material to spoil. | m2 |  | 0 | 0 |  | You can change the description in the yellow cells to better repreesent your works
EMBANKMENT CONSTRUCTION
Ee_302.01 | Cut & Fill operation, remove and spoil excess fill material on or near site | m3 |  | 0 | 0
Ee_302.02 | Foundation Preparation & Import 250mm nominal Fill/Subgrade. Mix, Place, Compact and Trim. | m2 |  | 0 | 0
Ee_302.03 | Stabilisation of subgrade with any stabilisation agent includes the process to remove and replace pavement if required | m2 |  | 0 | 0
To Main Summary |  |  |  |  | 0
DRAINAGE
Item | Description | Unit | Qty | Rate | Amount
402 - SURFACE DRAINS AND LEVEES
Dd_402.01 | Install, Remove, Repair, Reinstate, Maintain surface drains or levees | m | 6800 | 0 | 0
403 - SUBSOIL DRAINS
Ds_403.01 | Installation of drainage layer under pavement | m2 |  | 0 | 0
Ds_403.02 | Installation of subsoil drainage intersecting and redirecting water flow outside of pavement | m |  | 0 | 0
404 - CULVERTS
Dc_404.01 | Installation, Repair, Replacement of RCP culverts | Ea |  | 0 | 0
Dc_404.02 | Installation, Repair, Replacement of RCB culverts | Ea |  | 0 | 0
Dc_404.03 | Installation, Repair, Replacement of all other culvert types | Ea |  | 0 | 0
405 - DRAINAGE STRUCTURES
Dm_405.01 | Installation, Repair, Replacement, Cleaning of Manholes, Gullies, Catch Pits | Ea |  | 0 | 0
406 - ROCK PROTECTION
Dr_406.01 | Installation, Removal, Repair, Replacement of Rock Protection | m2 |  | 0 | 0
407 - KERBING
Dk_407.01 | Installation, Removal, Repair, Replacement of Kerbing | m |  | 0 | 0
Dk_407.02 | Installation, Removal, Repair, Replacement of Kerb openings | Ea |  | 0 | 0
Dk_407.03 | Installation, Removal, Repair, Replacement of Traffic Islands or Medians | Ea |  | 0 | 0 | 0
To Main Summary |  |  |  |  | 0
PAVEMENTS AND SURFACING | SERIES 300 - EARTHWORKS
Item | Description | Unit | Qty | Rate | Amount
501 - PAVEMENT
Ps_501.01 | Import Gravel for Subbase, Mix, Place, Compact and Trim includes topup. | m2 |  | 0 | 0
Ps_501.02 | Stabilisation of Subbase, Mix, Compact and Trim, includes wet mixing with rotary drum. | m2 |  | 0 | 0
Ps_502.01 | Import Gravel for Basecourse, Mix, Place, Compact and Trim includes topup. | m2 |  | 0 | 0
Ps_502.02 | Stabilisation of Basecourse, Mix, Compact and Trim, includes wet mixing with rotary drum. | m2 |  | 0 | 0
503 - BITUMEN SEALING
Pb_503.01 | Prime | m2 |  | 0 | 0
Pb_503.02 | Double/Double 14/7 | m2 |  | 0 | 0
Pb_503.03 | Widening of seal using jet patcher | m2 |  | 0 | 0
504 - ASPHALT WEARING COURSE
Pa_504.01 | Laying, Compaction, Repair, Tie-ins, of Asphalt | m2 |  | 0 | 0 | 0
To Main Summary |  |  |  |  | 0
TRAFFIC FACILITIES
Item | Description | Unit | Qty | Rate | Amount
601 - SIGNAGE
Ts_601.01 | Install rubbish bins | Ea |  | 0 | 0
Ts_601.02 | Installation, Removal, Replacement, Repair all signage | Ea |  | 0 | 0
602 - GUIDEPOSTS
Tg_602.01 | Installation, Removal, Replacement, Guideposts | Ea | 150 | 0 | 0
603 - SAFETY TRAFFIC BARRIER SYSTEMS
Tb_603.01 | Installation of Safety Traffic Barrier System | m |  | 0 | 0
Tb_603.02 | Removal, Replacement, Repair of Safety Traffic Barrier System | m |  | 0 | 0
604 - LINEMARKING
Tl_604.01 | Mobilisation Linemarking Crew linemarking | Ea |  | 0 | 0
Tl_604.02 | Install Linemarking all types oif linemarking | m |  | 0 | 0
Tl_604.03 | Install, Replace, Repair painted islands and gore marking | m2 |  | 0 | 0
Tl_604.04 | Install, Replace, Repair Holding Lines | m |  | 0 | 0
605 - GRABS RAILS AND BOLLARDS
Tr_605.01 | Installation, Removal, Replacement, Repair Grabs Rails and Bollards | Ea |  | 0 | 0 | 0
To Main Summary |  |  |  |  | 0
MISCELLANEOUS
Item | Description | Unit | Qty | Rate | Amount
903 - FENCING
Mf_903.01 | Install Fencing may include Repair, Remove, Replace Fencing and contract quote | m |  | 0 | 0
Mf_903.02 | Repair, Remove, Replace Fencing generally inhouse | m |  | 0 | 0 | 0
To Main Summary |  |  |  |  | 0
Item | Description | Unit | Qty | Rate | Amount
SCHEDULE 2 - PROVISIONAL SUMS
DELAY and DISRUPTION
PS_01 | Allow the Provisional Sum for | Ea |  | 0 | 0 | 0
To Main Summary |  |  |  |  | 0

## Cost Breakdown
Shire of xxx/ road SLK to | [6 empty] | Notes on filling out Template Hide this Column to add notes of your own
QUOTE TEMPLATE |  |  |  |  | 0 |  | Data entry only in yellow cells
GENERAL REQUIREMENTS | [6 empty] | Some Items have been filled for convenience and or as a guide
|  | CONDITIONS of CONTRACT |  | Mark up | 0%
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | This is a Private Contractor item for Civil Construction to cover insurance costs Shires might not claim this if costs are absorbed elsewhere
GR_01 |  | Cost of Certificates of currency to sustain the contractual obligations. | Sum | 1 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
1 | 0% | Percentage of Construction Cost | Sum | 1 | 0 | 0
Total | [5 empty] | 0
UTILITIES and SERVICES
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | This is to capture location of utilities. Predominantly this will require a DB4D search and an approved location contractor Costs to protect is also looked at
GR_02 |  | Location, Relocation, Protection of Utilities and Services | Sum | 1 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
MOBILISATION and DEMOBILISATION of PERSONNEL, PLANT and EQUIPMENT
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Mobilisation is cost that gets forgotten more than not Shires will probably do most in house in which case Operator and Float hours should be included. Some items of mob will be captured in the individual codes especially if it is part of a quote
GR_03 | Contractor Equipment Labour Material | Cost relating to in mobilisation and Demobilisation of Personnel, Plant and Equiptment to and from the worksite facilities.(including their RDO breaks) | Sum | 1 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
SITE FACILITIES (Accommodation and Meals)
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Accommodation will be non existant for Shires however sometimes contractors will need accom, it might also be cheaper for shire to supply accom Fill this Item in if shire is supplying accom
GR_04 | Contractor Equipment Labour Material | Cost relating to accommodation, meals, maintenance and Management of the on-site facilities for the duration of the contract. | Sum | 1 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
|  |  | 0 |  | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
SURVEY and AS-CONSTRUCTED RECORDS
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Surveyor Costs and Items will come straight from quote - add these items in the Rates 1st tab Surveyors charges are usually broken down Alternatively a full quote might be provided As Constructed if needed are captured here
GR_05 | Contractor Equipment Labour Material | Cost of Setting out the works and the Submmission of the As-Constructed records and plans | Sum | 1 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
MANAGEMENT and SUPERVISORY REQUIREMENTS
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | As the description says anything to do with Management and Supervision of the project including development and submission of this quote
GR_06 | Contractor Equipment Labour Material | Cost of relating to preparation, submission, implementation, execution and supervision of the Construction / Project Management Plan and Construction programme | Weeks |  | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
QUALITY ASSURANCE and TESTING
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Soil Testing Costs and Items will come straight from quote - add these items in the Rates 1st tab Soil Testing charges are usually broken down Alternatively a full quote might be provided
GR_07 | Contractor Equipment Labour Material | Cost of Quality Assurance Testing, pavement testing by NATA approved company | Item | 1 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
OCCUPATIONAL SAFETY and HEALTH
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Costs for Maintaining Safety on the project, this includes equipment, plans, safety adviser. Usually this is absorbed by the Shire overheads component.
GR_08 | Contractor Equipment Labour Material | Cost relating to the preparing, submitting, reviewing updating implementing and maintaining the Occupational Safety and Health Plan for the duration of the contract. | Sum | 1 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
ENVIRONMENTAL REQUIREMENTS
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | This can include DWER constraints and the costs to implement the plan. Protection of DRF sire ie fences etc
GR_09 | Contractor Equipment Labour Material | Cost relating to the preparing, submitting, reviewing updating implementing and maintaining the Environmental Management Quality Plan for the duration of the contract. | Sum | 1 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
TRAFFIC MANAGEMENT REQUIREMENTS
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Includes Traffic Control either inhouse or contract all TC travel also Plans costs of building submitting and review
GR_10 | Contractor Equipment Labour Material | Cost relating to the preparing, submitting, reviewing updating implementing and maintaining the Traffic Management Plan for the duration of the contract. | Sum | 1 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
PIT REHABILITATION
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Not just for Gravel pits but also stockpile sites that require clean up eg. Aggregate dump sites
GR_11 | Contractor Equipment Labour Material | Cost of rehabilitation of Stockpile and or Borrow Pit Area | Sum | 1 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
CONSTRUCTION WATER
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Cost of purchase Hiring bore pump, genset etc
GR_12 | Contractor Equipment Labour Material | Costs Relating to the Provision of construction water | Sum | 1 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
EARTHWORKS
301 - CLEARING
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Includes any quotes for clearing contractors. NB: does not include permits see GR 09
Ec_301.01 | Contractor Equipment Labour Material | Clear and cut the designated construction area, and table drains of all vegetation and topsoil material to spoil. | m2 | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
302 - EMBANKMENT CONSTRUCTION
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Embankment is any cut and fill of the layer below subgrade
Ee_302.01 | Contractor Equipment Labour Material | Cut & Fill operation, remove and spoil excess fill material on or near site | m3 | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Ee_302.02 | Contractor Equipment Labour Material | Foundation Preparation & Import 250mm nominal Fill/Subgrade. Mix, Place, Compact and Trim. | m2 | 0 | 0 | 0 | Subgrade is the top 150mm underneath the pavement layer it is generally the first selected and imported layer predominantly the Wheatbelt roads subgrade and embankment are the same Subgrade CBR is one critical item required for pavement design.
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Ee_302.03 | Contractor Equipment Labour Material | Stabilisation of subgrade with any stabilisation agent includes the process to remove and replace pavement if required | m2 | 0 | 0 | 0 | Stabilisation of the subgrade If the pavement layer has to be removed, set aside and then replaced this cost is also included
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
DRAINAGE
402 - SURFACE DRAINS and LEVEES
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Table drain and diversion banks Predominantly in the Wheatbelt there is no to very limited offshute drains
Dd_402.01 | Contractor Equipment Labour Material | Install, Remove, Repair, Reinstate, Maintain surface drains or levees | m | 6800 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
403 - SUBSOIL DRAINS
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Pavement is from hinge to hinge Subsoil is nearly always installed below the subgrade layer geotextiles, Filler material, pipe,
Ds_403.01 | Contractor Equipment Labour Material | Installation of drainage layer under pavement | m2 | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Ds_403.02 | Contractor Equipment Labour Material | Installation of subsoil drainage intersecting and redirecting water flow outside of pavement | m | 0 | 0 | 0 | These are usually used to intersect water before ingress into the formation
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
404 - CULVERTS
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | RCP - Reinforced Concrete Pipe Old system was bevell and face New system is bell and spigot with "O" ring Precast Headwalls can be built for multiple barrells
Dc_404.01 | Contractor Equipment Labour Material | Installation, Repair, Replacement of RCP culverts | Ea | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Dc_404.02 | Contractor Equipment Labour Material | Installation, Repair, Replacement of RCB culverts | Ea | 0 | 0 | 0 | RCB - Reinforced Concrete Box predominantly lengths are 1.2m however some of the smaller sizes can come in 2.4m lengths Headwalls are usually cast insitu
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Dc_404.03 | Contractor Equipment Labour Material | Installation, Repair, Replacement of all other culvert types | Ea | 0 | 0 | 0 | HDPE - High Density Ply Ethylene Corrigated Iron Generally Pipe shape lengths vary Headwalls can be precast RCP for ease of installation
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
405 - DRAINAGE STRUCTURES
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | This is usually for with town sites where multiple catchment points into a single flow is required
Dm_405.01 | Contractor Equipment Labour Material | Installation, Repair, Replacement, Cleaning of Manholes, Gullies, Catch Pits | Ea | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
406 - ROCK PROTECTION
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Always placed on the outlet side of culverts and floodways highly recommended as an maintenance erosion control method rock needs to be of a certain size Main Roads has an applicable spec
Dr_406.01 | Contractor Equipment Labour Material | Installation, Removal, Repair, Replacement of Rock Protection | m2 | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
407 - KERBING
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Dk_407.01 | Contractor Equipment Labour Material | Installation, Removal, Repair, Replacement of Kerbing | m | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Dk_407.02 | Contractor Equipment Labour Material | Installation, Removal, Repair, Replacement of Kerb openings | Ea | 0 | 0 | 0 | Concentrate and direct the water to whatever system is installed surface drain or gully etc
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Dk_407.03 | Contractor Equipment Labour Material | Installation, Removal, Repair, Replacement of Traffic Islands or Medians | Ea | 0 | 0 | 0 | Painted islands are captured at item 604.03
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
PAVEMENTS and SURFACING
501 - PAVEMENT
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Pavement = Subbase + Base Course Subbase is the remaining depth after the basecourse thickness has been removed Subbase is predominantly the less than ideal + material from the base course pit
Ps_501.01 | Contractor Equipment Labour Material | Import Gravel for Subbase, Mix, Place, Compact and Trim includes topup. | m2 | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Ps_501.02 | Contractor Equipment Labour Material | Stabilisation of Subbase, Mix, Compact and Trim, includes wet mixing with rotary drum. | m2 | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Ps_502.01 | Contractor Equipment Labour Material | Import Gravel for Basecourse, Mix, Place, Compact and Trim includes topup. | m2 | 0 | 0 | 0 | Base Course is generally 150 to 200mm thick BC material has specific criteria that it has to meet in order to be called BC
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | BC should only be stabilsed if it does not meet the quality required to be BC Rotary drum machines must be used sparingly so that the larger size particles are not broken down too small
Ps_502.02 | Contractor Equipment Labour Material | Stabilisation of Basecourse, Mix, Compact and Trim, includes wet mixing with rotary drum. | m2 | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
503 - BITUMEN SEALING | [6 empty] | Prime is used to improve the adhesion between the BC and the seal It was combined with the first coat seal as a primer seal but is enjoying a resurgance Prime and Primer seal must have a period inbetween themselves and the next coat Eco Prime is a product that can be sealed the same day - NB has a single supplier monoploy
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Pb_503.01 | Contractor Equipment Labour Material | Prime | m2 | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | Double/Double means two coats of binder and two coats of stone. This item is for any seals, PMB, crumbed rubber, Class 320 to name a couple. The seal has a couple of primary functions 1. To keep the water out of the BC 2. To act as a wear layer for tyres A seal over 15 years should be inspected every year for stress and a resealed sheduled.
Pb_503.02 | Contractor Equipment Labour Material | Double/Double 14/7 | m2 | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | A jet patcher uses an emulsion and aggregate, single size normally, to form a type of insitu cold mix It should not be considered for any widening where the depth exceeds 20mm
Pb_503.03 | Contractor Equipment Labour Material | Widening of seal using jet patcher | m2 | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
504 - ASPHALT WEARING COURSE
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Pa_504.01 | Contractor Equipment Labour Material | Laying, Compaction, Repair, Tie-ins, of Asphalt | m2 | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
TRAFFIC FACILTIES
601 - SIGNAGE
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Ts_601.01 | Contractor Equipment Labour Material | Install rubbish bins | Ea | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | The WSFN signage should be in here Consider any other signs that have to be removed
Ts_601.02 | Contractor Equipment Labour Material | Installation, Removal, Replacement, Repair all signage | Ea | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
602 - GUIDEPOSTS | [6 empty] | Rule of Thumb for calculating guideposts 1. divid total project length by 300m 2. add number of culverts 3. divide total length of all curves by 50m i.e. TP to TP 4. double for the other side The result will be close enough for quoting purposes. NB crests and multi barrell culverts will require more posts
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Tg_602.01 | Contractor Equipment Labour Material | Installation, Removal, Replacement, Guideposts | Ea | 150 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
603 - TRAFFIC BARRIER SYSTEMS | [6 empty] | This item needs to be designed by a Road Traffic Engineer.
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Tb_603.01 | Contractor Equipment Labour Material | Installation of Safety Traffic Barrier System | m | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value | The existing system needs to be checked for Aust Standard compliance before it is replaced
Tb_603.02 | Contractor Equipment Labour Material | Removal, Replacement, Repair of Safety Traffic Barrier System | m | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
604 - LINEMARKING
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Tl_604.01 | Contractor Equipment Labour Material | Mobilisation Linemarking Crew linemarking | Ea | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Tl_604.02 | Contractor Equipment Labour Material | Install Linemarking all types oif linemarking | m | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Tl_604.03 | Contractor Equipment Labour Material | Install, Replace, Repair painted islands and gore marking | m2 | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Tl_604.04 | Contractor Equipment Labour Material | Install, Replace, Repair Holding Lines | m | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
605 - GRAB RAILS and BOLLARDS
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Tr_605.01 | Contractor Equipment Labour Material | Installation, Removal, Replacement, Repair Grabs Rails and Bollards | Ea | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
MISCELLANEOUS
903 - FENCING
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Mf_903.01 | Contractor Equipment Labour Material | Install Fencing may include Repair, Remove, Replace Fencing and contract quote | m | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
Mf_903.02 | Contractor Equipment Labour Material | Repair, Remove, Replace Fencing generally inhouse | m | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0
PROVISIONAL SUM |  |  | PROVISIONAL SUM |  |  |  | Traditionally Main Roads uses this item for "unsuitable material" Wheatbelt shire have the 10% contingency instead
Project Item | Resource | Description of Project Item | Unit of Item | Qty of Item | Rate of Item | Item Quote Value
PS_01 | Contractor Equipment Labour Material | Allow the Provisional Sum for | Ea | 0 | 0 | 0
Qty of Resource | Resource | Details of Resource | Units of Resource | Qty of units | Rate of Resource | Resource Cost
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
|  |  | 0 |  | 0 | 0
Total | [5 empty] | 0

## Utilisation (hidden)
Contractor | Scheduled Hours | Equipment | Scheduled Hours | Labour | Scheduled Hours
0 | 0 | 0 | 0 | 0 | 0

## UtilisationPQ
Resource | Details of Resource | Units of Resource | Utilisation
Important!
Everytime you open this sheet.
1. Left Click inside the table
2. Left Click the "Query" tab
3. Left Click "Refresh"

## Method Statement
| Method Statement and task sequence | Risks | Controls
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26

## Project Planner
Project Planner |  |  |  | Shire of xxx/ road SLK to
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200
| 10 | 5 | 5 | 4 | 50%
| 1 | 6 | 1 | 6 | 0%
| 2 | 4 | 2 | 5 | 0%
| 4 | 8 | 4 | 6 | 0%
| 4 | 2 | 4 | 8 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%

## Assumptions
ASSUMPTIONS | Shire of xxx/ road SLK to
Project Specific
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## R&O
RISK & OPPORTUNITY REGISTER
Shire of xxx/ road SLK to |  |  |  |  | Project Manager: |  |  | Assessment As At: |  |  |  | Assessment Scope:
Date Reported | Opportunity / Risk | Open / Closed | Opportunity / Risk Title | Description | Type (Key Element) | Maximum / Current Opportunity $ | Maximum / Current Risk $ | Logic of Maximum / Current Risk / Opportunity | Current Likelihood | Current Consequence | Current Rating | Mitigation (Treatments) / Maximisation Strategy | Most Likely Outcome / Residual Opportunity $ | Most Likely Outcome / Residual Risk $ | Residual Likelihood | Residual Consequence | Residual Rating
2011-12-01 | Risk | Open | Rocks | Rock within works requiring removal | 3. Finance |  | 0 | no formal investigation undertaken |  |  | L4 | Source rock breaker attachment |  | 0 | Possible 10-33% | Insignificant <$50K | L4
2011-12-01 | Opportunity | Open | Programming of works | Sealing to be undertaken in conjunction with 8 other sites- reduce mobilisation | 3. Finance | 0 |  |  |  |  | M11 | Program P-Bay at GNH 1164 to coincide with this work | 0 |  | Likely 33-80% | Minor $50K-<$0.5M | M11
2011-12-01 | Risk | Open | Surfacing | Full service sealing crew required | 3. Finance |  | 0 | Unable to be self sufficient in precoating, sweeping and rolling |  |  | L4 | Planning |  | 0 | Possible 10-33% | Insignificant <$50K | L4
[7 empty] | Total of Most Likely Outcome Opportunity / Residual $ | [5 empty] | 0
[8 empty] | TOTAL OF Most Likely Outcome / Residual Risk $ | [5 empty] | 0
[8 empty] | NET TOTAL of Most Likely Outcome / Residual $ | [5 empty] | 0
NOTES: Focus is on up to the TOP 10 risks and up to the TOP 10 opportunities. Process: Project completes the forecast cost to complete incorporating risks with 100% likelihood (Events are certain to happen). All risk & opportunities with likelihood of
[18 empty] | Opp or Risk | Open or Closed | Key element | Likelihood | Consequence | Assessment Scope | MATRIX | Consequence
[18 empty] | Opportunity | Open | 1. Commercial/Legal | Almost Certain >80% | Insignificant <$50K | Project - Risks to completed project cost results | Likelihood | Insignificant <$50K | Minor $50K-<$0.5M | Moderate $0.5M-<$1M | Major $1M-<$5M | Critical >$5M
[18 empty] | Risk | Closed | 2. Engineering/Technical | Likely 33-80% | Minor $50K-<$0.5M | Project - Risks to ISA TARP costs at completion | Almost Certain >80% | M11 | H16 | H20 | VH23 | VH25
[20 empty] | 3. Finance | Possible 10-33% | Moderate $0.5M-<$1M | Project - Macmahon EBIT Share of JV/Alliance R&O Register | Likely 33-80% | M7 | M12 | H17 | H21 | VH24
[20 empty] | 4. HSEQ | Unlikely 2-10% | Major $1M-<$5M | Division Results - Risk of current forecast to achieve FY Budget | Possible 10-33% | L4 | M8 | M13 | H18 | H22
[20 empty] | 5. HR/IR | Rare 1%< | Critical >$5M |  | Unlikely 2-10% | L2 | L5 | M9 | M14 | H19
[20 empty] | 6. Information Technology |  |  |  | Rare 1%< | L1 | L3 | L6 | M10 | H15
7. Plant and Equipment
8. Political
9. Reputation
10 Supply/Procurement
11. Tendering/Estimating
12. Schedule (Time)
13. Other

## Drainage
Historically note; | [14 empty] | List of culvert materials | Coverage
Where water has topped the road during a rain event |  |  | Check for culverts, blocked?, too small?, downstream is clear? | [6 empty] | Type | Length | Lay length | Wall thickness | Backfill options | Corrigated Steel | 500
Scoured the table drain or dumped debrii on the road |  |  | Where can the water be diverted to?, options to eliminate scouring? | [6 empty] | Corrigated 6 | 6 | 5.9 | 3 |  | Plastic | 500
Lain for a period of time ie days or weeks |  |  | Blocked table drain?, requires culvert? | [6 empty] | Plastic 6 | 6 | 5.9 | 20 | Stab Sand | RCB | 200
[10 empty] | RCB 1.2 | 1.2 | 1.23 | 75 | Gravel | RCP | 200
Points to remember | [9 empty] | RCB 2.4 | 2.4 | 2.43 | 75
Coverage - minimum coverage allowable, if it cannot be achieved then another option has to be sourced | [6 empty] | Concrete - 200mm |  | PVC plastic etc - 500mm | RCP 1.2 | 1.2 | 1.14 | 50
Back fill - should be cement stabilised, sand or gravel material | [9 empty] | RCP 2.4 | 2.4 | 2.34 | 50 |  |  | 100
Rock protection - should be placed on outlet at end of apron ideally with a cutoff wall | [14 empty] | Culvert sizes | RCP
Length of culvert - culvert should be of sufficient length that the headwall is at least 2.5m from travel path of vehicles | [14 empty] | 300 | 0.12566
[15 empty] | 375 | 0.17721
Pipe Culverts | [14 empty] | 450 | 0.23758
Minimum Length of Culvert | 11 | m |  | Seal |  | Coverage | [8 empty] | 600 | 0.38485
Material constructed | Plastic | 500 |  | Basecourse | [10 empty] | 750 | 0.56745
Number of barrells | 2 |  |  | Subbase | [10 empty] | 900 | 0.7854
Length of sections | 6 | m |  | Subgrade | [10 empty] | 1200 | 1.3273
Number required | 4
Invert ( I )from seal | 900 | mm
Size | 450 | mm | [5 empty] | Backfill to top of subgrade
Coverage | 450 | mm
Pavement Thickness | 300 | mm
Backfill option | Stab Sand
Width | 1.6 | m
Minimum Volume of trench | 15.84 | m3
Minimum Volume of backfill required | 10.6132 | m3 |  | Invert ( I )
Cement Required 6% | 0.63679 | m3 |  | Bedding 100mm
| 0.95519 | tonnes
Bedding Volume +10% | 1.936 | m3
Box Culvert
Minimum Length of Culvert | 14.4 | m |  | Seal |  | Coverage
Material constructed | RCB | #N/A |  | Basecourse
Number of barrells | 6 |  |  | Subbase
Length of sections | 1.2 | m |  | Subgrade
Number required | 72
Invert ( I )from seal | 1500 | mm
Size | 1200 | mm | [5 empty] | Backfill to top of subgrade
Coverage | 300 | mm
Pavement Thickness | 150 | mm
Backfill option | Stab Sand
Width | 9.4 | m
Minimum Volume of trench | 203.04 | m3
Minimum Volume of backfill required | 39.744 | m3 |  | Invert ( I )
Cement Required 6% | 2.3846 | m3 |  | Slab 200mm
| 3.577 | tonnes
Concret slab volume | 36.472 | m3
Steel | 364.72 | m2 | SL81 Sheets | 25.3278 | Two layers of steel

## ESA 3
ADT and ESA quick calculator for figures pulled from class matrix traffic count | [12 empty] | Fields for input
Set value fields
Calculated fields
Road Name | [7 empty] | Road Number
Average daily traffic
Count No. | Location SLK |  | Start date |  | End date |  | Duration days |  | All vehicles total |  | Daily average traffic for individual count
1 | [6 empty] | 0 |  |  |  | 0
2 | [6 empty] | 0 |  |  |  | 0
3 | [6 empty] | 0 |  |  |  | 0
4 | [6 empty] | 0 |  |  |  | 0
5 | [6 empty] | 0 |  |  |  | 0
|  |  | TOTALS |  |  | Duration (No. of days) | 0 |  | 0 |  | Total vehicles
Figure required for WSFN MCA | [5 empty] | Average Daily traffic count for full sample (ADT) | [5 empty] | 0
Equivalent standard axles | [13 empty] | Main Roads WA Road Classification | Axle Equivalency Factor By Vehicle Class
Austroads | Class 1 | Class 2 | Class 3 | Class 4 | Class 5 | Class 6 | Class 7 | Class 8 | Class 9 | Class 10 | Class 11 | Class 12 |  |  | Class 3 | Class 4 | Class 5 | Class 6 | Class 7 | Class 8 | Class 9 | Class 10 | Class 11 | Class 12
RAV | Class 8: RAV 1; Class 9: RAV 2, 3; Class 10: RAV 4, 5; Class 11: RAV 6, 7; Class 12: RAV 9, 10 | [7 empty] | RAV 1 | RAV 2, 3 | RAV 4, 5 | RAV 6, 7 | RAV 9, 10
Count 1 | [13 empty] | Rural National Highways | 0.77 | 2.57 | 4.23 | 2.29 | 1.59 | 3.4 | 4.2 | 8.08 | 10.03 | 11.54
Count 2 | [13 empty] | Rural Highways | 0.77 | 2.57 | 4.23 | 2.29 | 1.59 | 3.4 | 4.2 | 8.08 | 10.03 | 11.54
Count 3 | [13 empty] | Rural Main and Secondary Roads | 0.23 | 1.09 | 3.24 | 0.96 | 0.6 | 2.9 | 3.13 | 5.64 | 7.26 | 7.87
Count 4 | [13 empty] | Urban Freeways and Highways | 0.68 | 2.3 | 2.67 | 1.3 | 1.48 | 2.95 | 3.42 | 4.74 | 5.84 | 6.98
Count 5 | [13 empty] | Other Important Urban Arterial Roads | 0.68 | 2.3 | 2.67 | 1.3 | 1.48 | 2.95 | 3.42 | 4.74 | 5.84 | 6.98
Total traffic | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Consessional Loading | 0.77 | 2.57 | 4.23 | 2.29 | 1.59 | 4 | 12.25 | 12.25 | 15 | 18
Multiplyer | 0 | 0 | 0.77 | 2.57 | 4.23 | 2.29 | 1.59 | 3.4 | 4.2 | 8.08 | 10.03 | 11.54 |  | AMMS ESA rating
Concessional | 0 | 0 | 0.77 | 2.57 | 4.23 | 2.29 | 1.59 | 4 | 12.25 | 12.25 | 15 | 18
AMMS | Class 1: 0; Class 2: 0
Austroads ESAs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAV ESA's | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMMS ESA's | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | Total 1 to12
0
[10 empty] | 0 | Duration days
|  |  | Austroads |  | Average Daily ESA's |  |  |  |  | 0
Figure required for WSFN MCA | Class 3: RAV; Class 5: Concessional Daily ESA's; Class 11: WSFN summary.
AMMS daily ESA's
[5 empty] | Yearly | [6 empty] | Design ESA only considers one direction
[5 empty] | Design Life |  | 40 | Growth | 3%
WSFNesa

## Resource Plan (hidden)
Quote Template
Resource Plan | People
TLC Contracting
Cat 12H Grader and Operator | Kevin
Cat 950 Loader and Operator | Dayrate
30,000L Semi Watercart and Operator | Richard
1 x Double Roadtrains and Operators | Bob
1 x Double Roadtrains and Operators | Colin
6 man Mobile Camp
Multi Tyred Roller | Dayrate
Smooth Drum Roller | Dayrate
Padfoot Roller | Dayrate
Excavator | Hr
Coates Hire
Fuel Trailer
RnR
Bitumen Sprayer and Operator
Aggregate Spreaders and Operators
TLC
Multi Tyred Roller and Operator
Loader
Broom and Operator
ISA
Site Manager and Ute | Mark
Supervisor and Ute
1 x Labourers/Operators | Eric Upston
1 x Labourers/Operators | Mark Billing
1 x Labourers/Operators | Andrew White
Base in MRWA Office, South Hedland Admin person
Base in MRWA Office, South Hedland Safety person

## Cartage Calcs
Fill in the yellow cells with your information
Fill material |  |  | 0 | m3 | Length (m) | Width (m) | Depth (m)
Material MDD |  | t/m3 | 0 | Tonnes Dry
Compaction Factor | 1.4 |  | 0 | Tonnes Pit | Hrs /day
Allowance (waste) | 10% |  |  |  | RT/Truck Cap |  | Pit weight | 0 | Rule of Thumb for Road Trains needs to be adjusted for corners, intersections, gravel roads etc
Average SLK of Worksite |  |  | #DIV/0! | Tip Rate |  | % moisture in Pit |  | 2% | Distance to Cart km | Ave Speed km/hr
SLK of Gravel Pit | [8 empty] | 0 to 10 | 45
Travel for trucks to and from pit |  | km | [6 empty] | 10 to 20 | 50
Average truck travel speed |  | km/hr | [6 empty] | 20 to 30 | 55
Truck travel time | #DIV/0! | hr | [6 empty] | 30 to 40 | 60
Loading time | 0.16667 | hr | Loading time | 10 | mins |  |  |  | 40 to 50 | 65
Tipping time | 0.083333 | hr | Tip Time | 5 | mins |  |  |  | 50 to 60 | 70
Total time per load | #DIV/0! | hr | [6 empty] | 60 to 70 | 75
Total loads per day | #DIV/0! | loads/day | [6 empty] | 70 to 80 | 80
Truck capacity | #DIV/0! | m3 | compacted | [5 empty] | 80 to 90 | 85
Total cartage per day (1 Truck) | #DIV/0! | m3/day | [6 empty] | 90 to 100 | 90
Total cartage per day all Trucks | #DIV/0! | m3/day | No of Trucks | [5 empty] | 100+ | 95
Total import vol.+ waste | 0 | m3 | #DIV/0! | m/day
Total cartage time in Days | #DIV/0! | days
Total cartage time Hours | #DIV/0! | hr
Basecourse |  |  | 0 | m3 | Length (m) | Width (m) | Depth (m)
Material MDD |  | t/m3 | 0 | Tonnes Dry
Compaction Factor | 1.4 |  | 0 | Tonnes Pit | Hrs /day
Allowance (waste) | 10% |  |  |  | RT/Truck Cap |  | Pit weight | 0 | Rule of Thumb for Road Trains needs to be adjusted for corners, intersections, gravel roads etc
Average SLK of Worksite |  |  | #DIV/0! | Tip Rate |  | % moisture in Pit |  | 2% | Distance to Cart km | Ave Speed km/hr
SLK of Gravel Pit | [8 empty] | 0 to 10 | 45
Travel for trucks to and from pit |  | km | [6 empty] | 10 to 20 | 50
Average truck travel speed |  | km/h | [6 empty] | 20 to 30 | 55
Truck travel time | #DIV/0! | hr | [6 empty] | 30 to 40 | 60
Loading time | 0.16667 | hr | Loading time | 10 | mins |  |  |  | 40 to 50 | 65
Tipping time | 0.083333 | hr | Tip Time | 5 | mins |  |  |  | 50 to 60 | 70
Total time per load | #DIV/0! | hr | [6 empty] | 60 to 70 | 75
Total loads per day | #DIV/0! | loads/day | [6 empty] | 70 to 80 | 80
Truck capacity | #DIV/0! | m3 | [6 empty] | 80 to 90 | 85
Total cartage per day (1 truck) | #DIV/0! | m3/day | [6 empty] | 90 to 100 | 90
Total cartage per day all trucks | #DIV/0! | m3/day | No of Trains | [5 empty] | 100+ | 95
Total import vol.+ waste | 0 | m3 | #DIV/0! | m/day
Total cartage time days | #DIV/0! | days
Total cartage time hours | #DIV/0! | hr
|  |  | 0 | m3 | Length (m) | Width (m) | Depth (m)
Material MDD |  | t/m3 | 0 | Tonnes Dry
Compaction Factor | 1.4 |  | 0 | Tonnes Pit | Hrs /day
Allowance (waste) | 10% |  |  |  | RT/Truck Cap |  | Pit weight | 0 | Rule of Thumb for Road Trains needs to be adjusted for corners, intersections, gravel roads etc
Average SLK of Worksite |  |  | #DIV/0! | Tip Rate |  | % moisture in Pit |  | 2% | Distance to Cart km | Ave Speed km/hr
SLK of Gravel Pit | [8 empty] | 0 to 10 | 45
Travel for trucks to and from pit |  | km | [6 empty] | 10 to 20 | 50
Average truck travel speed |  | km/hr | [6 empty] | 20 to 30 | 55
Truck travel time | #DIV/0! | hr | [6 empty] | 30 to 40 | 60
Loading time | 0.16667 | hr | Loading time | 10 | mins |  |  |  | 40 to 50 | 65
Tipping time | 0.083333 | hr | Tip Time | 5 | mins |  |  |  | 50 to 60 | 70
Total time per load | #DIV/0! | hr | [6 empty] | 60 to 70 | 75
Total loads per day | #DIV/0! | loads/day | [6 empty] | 70 to 80 | 80
Truck capacity | #DIV/0! | m3 | compacted | [5 empty] | 80 to 90 | 85
Total cartage per day (1 Truck) | #DIV/0! | m3/day | [6 empty] | 90 to 100 | 90
Total cartage per day all Trucks | #DIV/0! | m3/day | No of Trucks | [5 empty] | 100+ | 95
Total import vol.+ waste | 0 | m3 | #DIV/0! | m/day
Total cartage time in Days | #DIV/0! | days
Total cartage time Hours | #DIV/0! | hr
|  |  | 0 | m3 | Length (m) | Width (m) | Depth (m)
Material MDD |  | t/m3 | 0 | Tonnes Dry
Compaction Factor | 1.4 |  | 0 | Tonnes Pit | Hrs /day
Allowance (waste) | 10% |  |  |  | RT/Truck Cap |  | Pit weight | 0 | Rule of Thumb for Road Trains needs to be adjusted for corners, intersections, gravel roads etc
Average SLK of Worksite |  |  | #DIV/0! | Tip Rate |  | % moisture in Pit |  | 2% | Distance to Cart km | Ave Speed km/hr
SLK of Gravel Pit | [8 empty] | 0 to 10 | 45
Travel for trucks to and from pit |  | km | [6 empty] | 10 to 20 | 50
Average truck travel speed |  | km/hr | [6 empty] | 20 to 30 | 55
Truck travel time | #DIV/0! | hr | [6 empty] | 30 to 40 | 60
Loading time | 0.16667 | hr | Loading time | 10 | mins |  |  |  | 40 to 50 | 65
Tipping time | 0.083333 | hr | Tip Time | 5 | mins |  |  |  | 50 to 60 | 70
Total time per load | #DIV/0! | hr | [6 empty] | 60 to 70 | 75
Total loads per day | #DIV/0! | loads/day | [6 empty] | 70 to 80 | 80
Truck capacity | #DIV/0! | m3 | compacted | [5 empty] | 80 to 90 | 85
Total cartage per day (1 Truck) | #DIV/0! | m3/day | [6 empty] | 90 to 100 | 90
Total cartage per day all Trucks | #DIV/0! | m3/day | No of Trucks | [5 empty] | 100+ | 95
Total import vol.+ waste | 0 | m3 | #DIV/0! | m/day
Total cartage time in Days | #DIV/0! | days
Total cartage time Hours | #DIV/0! | hr
|  |  | 0 | m3 | Length (m) | Width (m) | Depth (m)
Material MDD |  | t/m3 | 0 | Tonnes Dry
Compaction Factor | 1.4 |  | 0 | Tonnes Pit | Hrs /day
Allowance (waste) | 10% |  |  |  | RT/Truck Cap |  | Pit weight | 0 | Rule of Thumb for Road Trains needs to be adjusted for corners, intersections, gravel roads etc
Average SLK of Worksite |  |  | #DIV/0! | Tip Rate |  | % moisture in Pit |  | 2% | Distance to Cart km | Ave Speed km/hr
SLK of Gravel Pit | [8 empty] | 0 to 10 | 45
Travel for trucks to and from pit |  | km | [6 empty] | 10 to 20 | 50
Average truck travel speed |  | km/hr | [6 empty] | 20 to 30 | 55
Truck travel time | #DIV/0! | hr | [6 empty] | 30 to 40 | 60
Loading time | 0.16667 | hr | Loading time | 10 | mins |  |  |  | 40 to 50 | 65
Tipping time | 0.083333 | hr | Tip Time | 5 | mins |  |  |  | 50 to 60 | 70
Total time per load | #DIV/0! | hr | [6 empty] | 60 to 70 | 75
Total loads per day | #DIV/0! | loads/day | [6 empty] | 70 to 80 | 80
Truck capacity | #DIV/0! | m3 | compacted | [5 empty] | 80 to 90 | 85
Total cartage per day (1 Truck) | #DIV/0! | m3/day | [6 empty] | 90 to 100 | 90
Total cartage per day all Trucks | #DIV/0! | m3/day | No of Trucks | [5 empty] | 100+ | 95
Total import vol.+ waste | 0 | m3 | #DIV/0! | m/day
Total cartage time in Days | #DIV/0! | days
Total cartage time Hours | #DIV/0! | hr

## Sheet2 (hidden)
Total days |  | 2011-11-07 | 2011-11-08 | 2011-11-09 | 2011-11-10 | 2011-11-11 | 2011-11-12 | 2011-11-13 | 2011-11-14 | 2011-11-15 | 2011-11-16 | 2011-11-17 | 2011-11-18 | 2011-11-19 | 2011-11-20 | 2011-11-21 | 2011-11-22 | 2011-11-23 | 2011-11-24 | 2011-11-25 | 2011-11-26 | 2011-11-27 | 2011-11-28 | 2011-11-29 | 2011-11-30 | 2011-12-01 | 2011-12-02 | 2011-12-03 | 2011-12-04 | 2011-12-05 | 2011-12-06
22 | 22 | 2011-11-07 | 2011-11-08 | 2011-11-09 | 2011-11-10 | 2011-11-11 | 2011-11-12 | 2011-11-13 | 2011-11-14 | 2011-11-15 | 2011-11-16 | 2011-11-17 | 2011-11-18 | 2011-11-19 | 2011-11-20 | 2011-11-21 | 2011-11-22 | 2011-11-23 | 2011-11-24 | 2011-11-25 | 2011-11-26 | 2011-11-27 | 2011-11-28 | 2011-11-29 | 2011-11-30 | 2011-12-01 | 2011-12-02 | 2011-12-03 | 2011-12-04 | 2011-12-05 | 2011-12-06
Activities | Duration (Days) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 19 | 20 | 21 | 22 | 23
Mark Green Your Break | 7 | bar: 2011-11-11 to 2011-11-17
Macmahon People Your Break | 5 | bar: 2011-11-11 to 2011-11-14
TLC Contracting Your Break | 4 | bar: 2011-11-10 to 2011-11-13
Floodway North West Coastal Hwy SLK 1076
Subase |  | 2011-11-07: Grader,2xwatercarts Smooth,Multi,Padfoot Rollers
Subbhase Testing | bar: 2011-11-08
Basecourse |  | 2011-11-09: Grader,2xwatercarts Smooth,Multi,Padfoot Rollers
Basecourse Testing | bar: 2011-11-11
Rhs Table Drain and Cleanup |  | 2011-11-09: Grader,2xwatercarts Smooth,Multi
Sealing |  | 2011-11-13: RnR
Rip and Remove Side Track | bar: 2011-11-14
Lhs Table Drain and Cleanup | bar: 2011-11-14 to 2011-11-15
Demobilisation | bar: 2011-11-15
Milstream Python Pool intersection Resheating
Import and Cartage of sheating material |  | 2011-11-15: Loader, 2 x Double Rd Trains
Balance Sheating Material |  | 2011-11-16: Grader,2xwatercarts Smooth,Multi
Balance Imported Gravel, Wet Mix, Place and Compact using Smooth Drum & Multi |  | 2011-11-17: Grader,2xwatercarts Smooth,Multi
Reshape Table Drains |  | 2011-11-19: Grader,2xwatercarts Smooth,Multi
Clean up |  | 2011-11-20: Grader,2xwatercarts Smooth,Multi
Demobilisation | bar: 2011-11-20
D-Link Truck Parking Bay (Newman)
Mobilisation | bar: 2011-11-20
Clearing | bar: 2011-11-21
Cut to Fill | bar: 2011-11-22 to 2011-11-23
Subgrade | bar: 2011-11-24 to 2011-11-25
Subase | bar: 2011-11-26; 2011-11-28
Base | bar: 2011-11-29 to 2011-12-02
Sealing |  | 2011-12-05: RnR
Table Drains | bar: 2011-12-03
Clean up | bar: 2011-12-06
Demobilisation